## Sheet1
On the T.R.A.I.L. to Diabetes Prevention Grantee Timeline 2018-2019
Highlighted cells indicate tasks that must be done during the identified month and upon the identified date
Non-highlighted cells indicate tasks and activities that must be done during the grant year, but which sites can plan according to implementation plan
2018
August | Award Announcements
T.R.A.I.L. Budget formulation
September | Award period begins September 1, 2018
Participate in National Training Sept. 25-26 in Minneapolis, MN
Hold recruitment events for T.R.A.I.L. participants
Recruit volunteers and peer leaders to help with the program
Submit signed LOA, Implementation plan, and administrative paperwork to FirstPic, Inc and NCAI
Tracking of Club-wide daily physical activity begins
Begin program implementation and data collection implementation plan. Administer pre-test on first day of implementation.
October | Identify and meet with potential Community Health Partner. Secure and submit MOA to FirstPic, Inc by October 31, 2018
Hold recruitment events for T.R.A.I.L. participants as needed
Identify and recruit potential community speakers
Reach out to NCAI and FirstPic, Inc for any initial questions related to program implementation or finances
Begin planning two hands-on, healthy snack demonstrations.
Program sessions and data collection continues
Volunteers and peer leaders assist with program implementation
Daily Physical Activity Log(s) for September are due October 15, 2018
Daily Physical Activity Log(s) for October are due November 15, 2018
Expenses from September - October 2018: reimbursement requests due November 15, 2018
Program sessions and data collection continues.
Volunteers and peer leaders assist with program implementation
Finalize all compliance documentation
Quarter 1 ends
December | Quarter 2 begins
One program contact and financial contact must participate in Quarterly webinar support series on Decmber 11, 2018 at 2PM ET
Program sessions and data collection continues
Volunteers and peer leaders assist with program implementation
Quarter 1 Progress Report(s) are due December 14, 2018
Daily Physical Activity Log(s) for November are due December 14, 2018
2019
January | Program sessions and data collection continues.
Volunteers and peer leaders assist with program implementation
Daily Physical Activity Log(s) for December are due on January 15, 2019
Expenses from November - December 2018: reimbursement requests due January 15, 2019
February | Program sessions and data collection continues
Implement T.R.A.I.L. participant lead community education project during Chapter 11 (if implementation began in December).
Volunteers and peer leaders assist with program implementation
One program contact and financial contact must participate in Quarterly webinar support series on February 12, 2019 at 3PM ET
Daily Physical Activity Log(s) for January are due on February 15, 2018.
Quarter 2 ends
March | Quarter 3 begins
Program sessions and data collection continues
Volunteers and peer leaders assist with program implementation
Quarter 2 Progress Report(s) are due on March 15, 2018.
Daily Physical Activity Log(s) for February are due on March 15, 2019.
Expenses from January - February 2019: reimbursement requests due March 15, 2019.
April | Program sessions and data collection continues
Volunteers and peer leaders assist with program implementation
Daily Physical Activity Log(s) for March are due on April 15, 2019
May | Program sessions and data collection continues
Volunteers and peer leaders assist with program implementation
Club-wide daily physical activity continues. Daily Physical Activity Log(s) for April is due on May 15, 2019
Expenses from March - April 2019: reimbursement requests due May 15, 2019
One program contact and financial contact must participate in Quarterly webinar support series on May 14, 2019 at 3PM ET
Quarter 3 ends
June | Quarter 4 begins
Program sessions and data collection continues
Volunteers and peer leaders assist with program implementation
Quarter 3 Progress Report(s) are due June 17, 2019
Daily Physical Activity Log(s) for May are due on June 17, 2019
July | Volunteers and peer leaders assist with program implementation
Daily Physical Activity Log(s) for June are due on July 15, 2019
Expenses from May - June 2019: reimbursement requests due July 15, 2019
One program contact and financial contact must participate in Quarterly webinar support series on July 9, 2019 at 3PM ET
Collect all program data for submission in August including: pre-tests, post-tests, and Phyical Activity Challenges
Program sessions and data collection ends
August | Spend down all remaining 2018-2019 grant dollars
Daily Physical Activity Log(s) for July are due on August 15, 2019
Submit participant data including pre-and post-test and Physical Activity Challenges by August 23, 2019
Award period ends August 31, 2019
September | Quarter 4 Progress Report(s) due September 13, 2019
Expenses from July - August 2019: reimbursement requests due September 27, 2019